## Sheet1
Sprint | User Story | Task | Owner | Estimate (days) | Priority | Status | Dependencies | Notes
Sprint 1 - Data Prep | As a data engineer, I must ingest and standardize merged KYC dataset in Colab | Mount Drive, validate path, load merged_dataset.csv, handle missing values, normalize formats | Data Engineer | 3 | High | To Do | Merged dataset in Drive | Use drive.mount('/content/drive'), confirm path via Colab file browser; add fallback upload.
Sprint 1 - Data Prep | As an ML engineer, I must extract address text from AADHAR images | Implement OCR pipeline (Form Recognizer/Tesseract), preprocess images (deskew, denoise), parse address fields | ML Engineer (CV) | 4 | High | To Do | Sample AADHAR images in data/ | Prefer Azure Form Recognizer for production; add preprocessing functions.
Sprint 2 - Modeling | As an NLP engineer, I must fine-tune an NLP model for address parsing & verification | Create train/val/test splits, fine-tune model in Colab, log metrics (precision/recall/F1) | ML Engineer (NLP) | 7 | High | To Do | Preprocessed address text from Sprint 1 | Use transformers or Azure OpenAI embeddings; save tokenizer & model.
Sprint 2 - Modeling | As a GNN engineer, I must build graph-based fraud detection | Construct entity graph from merged dataset, implement GraphSAGE sampling, train GNN, evaluate recall/precision | ML Engineer (GNN) | 7 | High | To Do | Cleaned entity attributes (IDs, addresses, phones) | Use DGL or PyG; implement mini-batching for large graphs.
Sprint 3 - Integration | As a backend dev, I must wrap models into an API for real-time verification | Create FastAPI app, endpoints (/verify), integrate preprocessing and model inference, add sample tests | Backend Engineer | 5 | High | To Do | Saved NLP and GNN models from Sprint 2 | Include model versioning and input validation.
Sprint 3 - Integration | As a compliance engineer, I need alerting for high-risk cases | Implement alert pipeline (queue), dashboard hooks, compliance logging | DevOps/Compliance | 4 | Medium | To Do | API integration | Integrate with Slack/email and audit logs.
Sprint 4 - Deployment | As a devops engineer, I must deploy the system securely to Azure sandbox | Containerize services (Docker), deploy to Azure, configure secrets, TLS, DB encryption | DevOps | 5 | High | To Do | Completed API and models | Ensure RBAC, encryption at rest and in transit; legal sign-off for AADHAR.
Sprint 4 - Deployment | As QA, I must run end-to-end tests on AADHAR dataset | Run E2E tests: OCR->NLP->Face-match->GNN->Decision; log metrics and false positives | QA Engineer | 3 | High | To Do | Deployed sandbox environment | Record detailed logs for audits; include human-review workflow.
Documentation | As a project lead, I need project documentation and demos | Write README, API docs, sample notebook cells, and demo video | Project Lead | 3 | Medium | To Do | Working system components | Include instructions to run Colab and deploy FastAPI.